## Slide 1
IANA Stewardship Transition Process
09 March 2016

## Slide 2
Implementation Planning Update

## Slide 3: Post-Transition New Entities
VRSGN’s
RZMS code changes (parallel testing)
ICANN’s
RZMS code changes (parallel testing)
ICANN’s RZMS code changes (RZA)
RZMA ready for public review
Key Dates:
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
a
ICANN’s RZMS code changes (SLEs)
t
SLA targets defined
SLA dashboard ready
Start
parallel testing
Remove RZA Role in production RZMS
RZMS, RZMA & Names SLEs
 | Project | Description | Plan Completion Date | Status | % Complete
 | RZMS changes to remove RZA role and support parallel testing | Remove NTIA's authorization process from RZMS (code changes for ICANN and Verisign, and parallel testing). | 09/30/15 08/15/16 |  | 
 | Names SLEs (SLEs for Naming Community) | RZMS code changes to accommodate new SLEs, inclusion of performance targets in ICANN-PTI contract, dashboard reporting of SLAs. | 09/30/15 08/15/16 |  | 
 | RZMA (Agreement with Root Zone Maintainer) | Completion of draft RZMA. | 01/31/16 02/29/16 |  | 
40%
03/08/16
Status As Of Date:
15%
Project Updates: Met with DT-A on 07 March to agree on future work phases and approach Met with Verisign to finalize the remaining issues Plan completion date for RZMS and Names SLEs changed to 15 August due to NTIA’s requirement | Upcoming Activities: Finalize draft RZMA Begin tool development to aggregate and convert data | Open Items: Pending Verisign’s code changes to start parallel testing
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
90%
Insert SLAs into ICANN-PTI contract
* All dates are estimates
DRAFT for Discussion
Existing data Parsing conclusions shared
a
t
c
End
parallel testing
c
Notes: Look for different ways to display your data or text by using alternatives to simple bullets.
To adjust the number in the arrow to text or another number, click on the text box around the number, revise.
To add an arrow, click on the arrow, ensure the arrow is highlighted, COPY and PASTE and move to the desired placement, or DELETE if there are too many arrows.

## Slide 4
 | Project | Description | Plan Completion Date | Status | % Complete
 | PTI (Post-Transition IANA) | Formation of PTI entity: legal formation (incorporation of affiliate, filing for 501c3, drafting of contract, etc.) and operationalization of PTI entity (board nominations, budget, etc.). | 09/30/16 08/15/16 |  | 
PTI
10%
Updates: Working with CWG on engagement process to implement PTI Plan completion date for PTI changed to 15 August due to NTIA’s requirement | Upcoming activities: Engagement with CWG on PTI implementation | Open Items:
03/08/16
Status As Of Date:
DRAFT for Discussion
* All dates are estimates
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
PTI entity legally
formed
ICANN-PTI contract ready for public review
PTI budget adopted by ICANN Board
501c3 status ready
PTI implementation plan ready for public review

## Slide 5
IPR, RZERC, CSC & Escalation Processes
 | Project | Description | Plan Completion Date | Status | % Complete
 | IANA IPR | Transfer of IANA IPR to a neutral trust. |  |  | 
 | RZERC (Root Zone Evolution Review Committee) | Formation of committee to advise ICANN Board on RZMS architectural and operational changes. | 09/30/16 08/15/16 |  | 
 | CSC (Customer Service Standing Committee) | Formation of committee to monitor PTI performance. | 09/30/16 08/15/16 |  | 
 | Escalation Processes | Updating of existing IANA operational complaint and escalation processes. | 09/30/16 08/15/16 |  | 
03/08/16
Status As Of Date:
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
Draft charter ready
CSC constituted
0%
Project Update: Working with CWG on engagement process to implement RZERC, CSC, and Escalation Processes Plan completion date for RZERC, CSC, and Escalation Processes changed to 15 August due to NTIA’s requirement | Upcoming Activities: Engagement with CWG on PTI implementation | Open Items: Waiting on implementation requirements for IANA IPR
DRAFT for Discussion
* All dates are estimates
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
RZERC implementation plan ready for review
CSC implementation plan ready for review
10%
10%
Escalation Processes implementation plan ready for review
10%

## Slide 6
Enhancing ICANN’s Accountability
 | Project | Description | Plan Completion Date | Status | % Complete
 | ICANN’s Bylaws | Updating of ICANN Bylaws. | 06/09/16 05/27/16* |  | 
 | IRP Enhancements | Implement enhancements to Independent Review Process. | 09/30/16 08/15/16 |  | 
 | RR Enhancements | Implement enhancements to ICANN's reconsideration request process. | 09/30/16 08/15/16 |  | 
 | Empowered Community Enhancements | Implement processes and mechanisms in support of the empowered community. | 09/30/16 08/15/16 |  | 
10%
Project Update: The representatives from the CWG, CCWG, NTIA, Board, and staff met 08 March to discuss Bylaws drafting process and timeline Plan completion date for all projects changed to 15 August due to NTIA’s requirement | Upcoming Activities: | Open Items: Final language of CCWG proposal
03/08/16
Status As Of Date:
0%
0%
0%
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
OCT
NOV
SEP
Key Dates:
c
Bylaws posted for public comments
a
ICANN Board adopts Bylaws
Key dates are based on assumption of proposals being delivered at ICANN55.
DRAFT for Discussion
* All dates are estimates
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
c
a
* Assuming a 90-days NTIA inter-agency review period

## Slide 7
Implementation of
CWG-Stewardship Proposal:
What does the ccNSO need to do?

## Slide 8: Post-Transition New Entities
Entity | Description | Occurrence | Classification
Customer Standing Committee (CSC) | To monitor the performance of the PTI | On-Going | Standing Committee
Root Zone Evolution Review Committee (RZERC) | To advise the ICANN Board of the architectural and operational changes to the root zone environment | As needed | Standing Committee
IANA Function Review Team (IFRT) | To review PTI’s SOW and PTI’s performance against ICANN-PTI contract and SOW | Periodic (Within 2 years from the transition, then no more than every 5 years thereafter) | Cross Community Working Group
Special IANA Function Review Team (Special IFRT) | To review the issues identified by CSC (only ccNSO and GNSO can initiate Special IFR) | As needed | Cross Community Working Group
Separation Cross-Community Working Group (SCWG) | To review the issues raised by the Special IFR and make recommendation | As needed | Cross Community Working Group
[CSC Charter Review] | To review CSC Charter | As needed (1 year after the first CSC meeting, then as requested thereafter) | Cross Community Working Group
[CSC Effectiveness Review] | To review the effectiveness of CSC | Periodic (2 years after the first CSC meeting, then every 3 years thereafter) | Cross Community Working Group
[CSC Service Level Target Review] | To review the requests of review or change to the service level targets | As needed | Cross Community Working Group

## Slide 9: Required Work for Transition
Appointment of CSC members
Approval of the whole composition of CSC
Appointment of RZERC member

## Slide 10: Timing of CSC Constitution
Mar
Apr
May
Jun
Sep
Aug
Jul
ICANN outreach
SO/ACs appoint candidates
ICANN sends SO/AC selected
candidates to ccNSO/GNSO
CSC constituted
Deadline
15
30
Expiration of IANA contract
ICANN submits implementation report to NTIA
Oct
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 11: Timing of RZERC Constitution
Mar
Apr
May
Jun
Sep
Aug
Jul
ICANN outreach
Candidates appointment
RZERC constituted
Deadline
15
30
Expiration of IANA contract
ICANN submits implementation report to NTIA
Oct
Notes: To adjust the length of each colored bar, click the bar, ensuring the bar is highlighted, grab a corner and length or shorten, depending on your preference.
To revise the type of timeline, revise the Month text boxes, all are editable.
To adjust the size of the black timeline lines, use the same procedure used to revise the colored bars.
The circles and text boxes beside the circles are also editable by clicking on the circle and/or text box.

## Slide 12: Customer Standing Committee (CSC)
CSC
Touch point with ccNSO
Reappointment due to recall or expiration of term
Activity:
Ongoing membership management
Touch point with ccNSO:
Review CSC escalated issues and decide whether to take further action with GNSO
Activity:
Monitor PTI performance against agreed service level targets
Touch point with ccNSO:
Provide briefing to the ccNSO and RySG 3 times a year (i.e. ICANN meeting)
Activity:
Provide regular updates to the direct customers of the IANA naming function
Members: ccTLD ROs | gTLD ROs | TLD Rep (non g/ccTLD)
Liaisons: GAC | NRL/ASO | RSSAC | SSAC | GNSO (non-registry) | ALAC | PTI

## Slide 13: Root Zone Evolution Review Committee (RZERC)
RZERC
Touch point with ccNSO
Reappointment due to recall or expiration of term
Activity:
Ongoing membership management
Touch point with ccNSO
TBD
Activity:
TBD per RZERC Charter
Members: ccNSO | GNSO RySG | ASO | IETF | RSSAC | SSAC | RZM
IFO | ICANN Board

## Slide 14: IANA Function Review Team (IFRT)
IFRT
Touch point with ccNSO
Appoint members from ccNSO
Appoint non-ccNSO ccTLD representative by consulting with Regional ccTLD Organizations
Activity:
Appoint member
Touch point with ccNSO
Provide ratification to IANA SOW amendment with GNSO
Activity:
Review and recommend changes to IANA SOW
Members: ccNSO | ccTLD (non-ccNSO) | RySG | RrSG
CSG | NSCG | RSSAC | GAC | ALAC | CSC

## Slide 15: Special IANA Function Review Team (Special IFRT)
Special IFRT
Touch point with ccNSO
Review CSC escalated issues with GNSO to determine whether to trigger a Special IFR
Activity:
N/A
Touch point with ccNSO:
Appoint members from ccNSO
Appoint non-ccNSO ccTLD representative by consulting with Regional ccTLD Organizations
Activity:
Appoint member
Touch point with ccNSO:
Approve the creation of the SCWG with GNSO
Activity:
Recommend the creation of the Separation Cross-Community Working Group (SCWG)
Members: ccNSO | ccTLD (non-ccNSO) | RySG | RrSG
CSG | NSCG | RSSAC | GAC | ALAC | CSC
Numbers Community | Protocol Community

## Slide 16: Separation Cross Community Working Group (SCWG)
SCWG
Touch point with ccNSO
Appoint members from ccNSO
Appoint non-ccNSO ccTLD representative by consulting with Regional ccTLD Organizations
Activity:
Appoint member
Members: ccNSO | ccTLD (non-ccNSO) | RySG | RrSG | CSG
NSCG | RSSAC | SSAC | GAC | ALAC | CSC | IFRT
Numbers Community | Protocol Community

## Slide 17: [CSC Charter Review]
[CSC Charter Review]
Members:
ccNSO
RySG
Touch point with ccNSO
Appoint representatives from ccNSO
Activity:
Appoint member
Touch point with ccNSO
Provide ratification to recommended changes with GNSO
Activity:
Make recommendation to change CSC Charter

## Slide 18: [CSC Effectiveness Review]
[CSC Effectiveness Review]
Members:
TBD
Touch point with ccNSO
Determine methods of review with GNSO
Activity:
TBD

## Slide 19: [CSC Service Level Target Review]
[CSC Service Level Target Review]
Members:
ccNSO
GNSO
Touch point with ccNSO
Provide ratification to proposed changes to service level targets with GNSO
Activity:
Recommend change to the service level targets

## Slide 20: ccTLD Community Work
CWG-Stewardship Proposal Paragraph 1106-6:
Appeal mechanism. An appeal mechanism, for example in the form of an Independent Review Panel, for issues relating to the IANA functions. For example, direct customers with non-remediated issues or matters referred by ccNSO or GNSO after escalation by the CSC will have access to an Independent Review Panel. The appeal mechanism will not cover issues relating to ccTLD delegation and redelegation, which mechanism is to be developed by the ccTLD community post-transition.